## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Marching Masters | [6 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Drexel CCI Senior Design | [6 empty] | On Track | [6 empty] | Low Priority | [6 empty] | Med Priority | [6 empty] | High Priority | [6 empty] | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  | Project Start Date: |  | 2020-09-22
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 21 |  |  | October | [20 empty] | November | [27 empty] | December
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-10-13 to 2020-12-21
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Progress | Start | End | No. Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Project Management
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Team Formation
| Team Member Assigned | Milestone | TEAM | 100% | 2020-09-22 | 2020-09-22 | 1
| Team Roles Assigned | Goal | TEAM | 100% | 2020-10-04 | 2020-10-04 | 1
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Project Planning
| Preliminary Project Plan | High | Aparna/Brandin | 100% | 2020-09-29 | 2020-10-13 | 15
| Project Plan (Baselined) | High | Aparna/Tumaris | 100% | 2020-10-14 | 2020-11-03 | 21
| Revised Project Plan | High | Aparna/Brandin | 100% | 2021-01-13 | 2021-01-19 | 7
Requirements Engineering
Customer Requirements
| Identify Potential User Groups | High | Brandin | 100% | 2020-09-29 | 2020-10-13 | 15
| Technology Research | High | Brandin/Aparna | 100% | 2020-09-29 | 2020-10-13 | 15
| Market Research | High | Adam/Tumaris | 100% | 2020-09-29 | 2020-10-13 | 15
| Conduct Focus Groups | High | Brandin | 100% | 2020-10-14 | 2020-10-20 | 7
| Key Assuptions | High | Aparna/Brandin | 100% | 2020-10-21 | 2020-10-24 | 4
| Customer Reqirements (Baselined) | High | Jeffer/Brandin | 100% | 2020-09-29 | 2020-10-27 | 29
Requirements Specification
| Requirements Specification | High | TEAM | 100% | 2020-10-28 | 2020-11-24 | 28
| Introduction/Description Sections | High | Brandin | 100% | 2020-10-28 | 2020-11-03 | 7
| Functional Requirements Section | High | Jeffer/Tumaris | 100% | 2020-10-28 | 2020-11-24 | 28
| Non-Functional Requirements Section | High | Aparna/Brandin | 100% | 2020-11-04 | 2020-11-24 | 21
| Wireframe/Mockup | High | Jeffer/Tumaris | 100% | 2020-11-11 | 2020-11-24 | 14
| Use Cases & Activity Diagram | High | Brandin | 100% | 2020-11-17 | 2020-11-24 | 8
| Reqirements Specification (Baselined) | High | Jeffer/Tumaris | 100% | 2020-11-25 | 2020-12-08 | 14
| Revise and Update from Feedback | Goal | TEAM | 100% | 2020-11-25 | 2020-12-08 | 14
Proof of Concept
| Research of Technologies | Med | Brandin/Aparna | 100% | 2020-10-06 | 2020-10-13 | 8
| Planning of Proof of Conecpt | Med | Adam/Siddharth | 100% | 2020-10-14 | 2020-10-20 | 7
| Development of Proof of Conecpt | Med | Jeffer/Adam/Siddharth | 100% | 2020-10-21 | 2020-12-11 | 52
| Testing of Proof of Concept | Med | Jeffer/Adam/Siddharth | 100% | 2020-12-11 | 2021-01-11 | 32
System Design
| System Design Document | High | TEAM | 0% | 2021-01-20 | 2021-02-09 | 21
| Introduction/Description Sections | High | Aparna | 0% | 2021-01-20 | 2021-01-22 | 3
| Design Overview Section | High | TEAM | 0% | 2021-01-20 | 2021-01-26 | 7
| UML Sections | High |  | 0% | 2021-01-27 | 2021-02-09 | 14
| Data Handling Section | High |  | 0% | 2021-02-03 | 2021-02-09 | 7
Software Implementation
Development of Front-End
| Application Log-In Page | High |  | 0% | 2021-02-10 | 2021-03-09 | 28
| Application Dashboard | High |  | 0% | 2021-02-10 | 2021-03-09 | 28
| Tracking Visualization | High |  | 0% | 2021-02-10 | 2021-03-09 | 28
| Viewing Documents/Events/Etc. | High |  | 0% | 2021-02-10 | 2021-03-09 | 28
| Send/Receive Feedback | High |  | 0% | 2021-02-10 | 2021-03-09 | 28
Development of Back-End
| Establishment of Database | High |  | 0% | 2021-02-10 | 2021-03-09 | 28
| User Handling | High |  | 0% | 2021-02-10 | 2021-03-09 | 28
| Uploading Documents/Events/Etc. | High |  | 0% | 2021-02-10 | 2021-03-09 | 28
| Position Tracking | High |  | 0% | 2021-02-10 | 2021-03-09 | 28
| Communication with Front-End | High |  | 0% | 2021-02-10 | 2021-03-09 | 28
Verification & Validation
| Test Approach and Constraints | High |  | 0% | 2021-04-01 | 2021-06-01 | 62
| Test Assumptions and Exclusions | High |  | 0% | 2021-04-01 | 2021-06-01 | 62
| Debugging | High |  | 0% | 2021-04-01 | 2021-06-01 | 62
| Automated Testing | Low |  | 0% | 2021-04-01 | 2021-06-01 | 62
| Internal Testing | High |  | 0% | 2021-04-01 | 2021-06-01 | 62
| Alpha Testing | High |  | 0% | 2021-04-01 | 2021-06-01 | 62
| Beta Testing | Med |  | 0% | 2021-04-01 | 2021-06-01 | 62
Other Deliverables
Project Presentations
| End Term Presentation (Fall) | Goal | Aparna/Brandin | 100% | 2020-11-11 | 2020-12-01 | 21 | W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2
| End Term Presentation (Winter) | Goal |  | 0% | 2021-02-24 | 2021-03-09 | 14
| End Term Presentation (Spring) | Goal |  | 0% | 2021-05-01 | 2021-06-01 | 32
Website
| Creation of Project Website | Goal | Brandin | 100% | 2020-10-13 | 2020-10-13 | 1 | T: 2
This is an empty row

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.